## Intro
This is the project register for the chexman project

## Decisions
Decisions | proposals | Status | Last Date | Outcome
App name | Living costs, EXA(employee expenses App), | Done | 2021-10-16 | Chexman
Tech stack | .NET PHP, Java | Done | 2021-10-23 | mysql, php,Android
Table names | logs and users/app_users | Done | 2021-11-21 | logs, app_users

## Dod
Story agreed
Code writen
Integration test
performance test
Documentation updated as per deliverable
Deliverable uploaded to github

## Backlog-Epics
Epic Code | Name | Description | Status | Last Date | Deliverables | Notes
E1 | Inception | Provision of basics startup artifacts to define project objectives | Done | 2021-10-27 | ReqSpec, OverviewMap and Project Register | Docs are available to commence work. Additional design odcs to be provided as required.
E2 | MVP | Implementation of basic app | Not started | 2021-10-27 | installable app

## Backlog-Stories
Story Code | Name | Description | Status | Owner | Plan | Actual | Notes
E1S1 | GitHubSet | Create a Github project and grant access to all team members. | Done | MLP | 2021-10-23 | 2021-10-23
E1S2 | ReqDoc | Write Requirement Specification document | Done | EIN | 2021-10-23 | 2021-10-23
E1S3 | FirstSteps | Identify and document all required startup activities | Done | JP | 2021-10-23 | 2021-10-23
E1S4 | Agree Coding Standards | Juanpe to review and all to agree and learn | Assgined | All
E1S5 | Define branching strategy | Based on github-flow but simpler | Assigned Jonatan | Maria | 2021-11-27
E2S1 | MVS Definition | Agree and document the MVS | Started | All
E2S2 | DB Log and User | Write the Log and User tables as per Req Spec | Assigned | Efi | 2021-11-27
E2S3 | Login Page | Write the login page | Assigned Jonatan |  | 2021-11-27
E2S4 | Define first cut style | First cut CSS for site | Assgined | Jonatan |  | 2021-11-21 | extracted to separate file
E2S5 | Log each user login into logs table | A db component to provide the required store procedure and a php page update to call it. | Assigned | Jonatan/Efi