## Decisions
Decisions | proposals | Status | Last Date | Outcome
App name | Living costs, EXA(employee expenses App), | Done | 2021-10-16 | Chexman
Tech stack | .NET PHP, Java | Done | 2021-10-23 | mysql, php,Android

## Dod
Code writen
Story updated
Integration test
performance test
Documentation updated as per deliverable
Deliverable uploaded to github

## Backlog-Epics
Epic Code | Name | Description | Status | Last Date | Deliverables | Notes
E1 | Inception | Provision of basics startup artifacts to define project objectives | Done | 2021-10-27 | ReqSpec, OverviewMap and Project Register | Docs are available to commence work. Additional design odcs to be provided as required.
E2 | MVP | Implementation of basic app | Not started | 2021-10-27 | installable app

## Backlog-Stories
Story Code | Name | Description | Status | Owner | Plan | Actual | Notes
E1S1 | GitHubSet | Create a Github project and grant access to all team members. | Done | MLP | 2021-10-23
E1S2 | ReqDoc | Write Requirement Specification document | Done | EIN | 2021-10-23
E1S3 | FirstSteps | Identify and document all required startup activities | Done | JP | 2021-10-23
E2S1 | MVS Definition | Agree and document the MVS | Started | All
E2S2 | DB Log and User | Write the Log and User tables as per Req Spec | Assigned | Efi
E2S3 | Login Page | Write the login page | Assigned Jonatan
E2S3 | Define first cut style | First cut CSS for site | Assgined | Jonatan
E2S4 | Agree Coding Standards | Juanpe to review and all to agree and learn | Assgined | All